## Launch Checklist
CONTROLWEAVE ¦ GTM Launch Checklist & Timeline
Q1–Q2 2026 • 90-Day Full-Launch Plan • Owner: Jaja Conteh / Conteh Consulting LLC
Phase | Week / Timeline | Task | Category | Owner | Due Date | Status | Notes
PHASE 0: FOUNDATION
Phase 0: Foundation | Weeks 1–2 | Finalize Railway one-click deploy and verify Community Edition runs end-to-end | Infrastructure | Jaja | 2026-03-06 | Done | Confirm health checks pass
Phase 0: Foundation | Weeks 1–2 | Publish Community Edition to GitHub (public repo) with polished README | Infrastructure | Jaja | 2026-03-06 | Not Started | Include Railway deploy button
Phase 0: Foundation | Weeks 1–2 | Build controlweave.com landing page: hero, pricing, CTA (“Deploy Free” + “Book a Demo”) | Marketing | Jaja | 2026-03-06 | Not Started | Framer or Webflow recommended
Phase 0: Foundation | Weeks 1–2 | Set up CRM (HubSpot free or Pipedrive); import initial 200 CISO prospect list | Sales | Jaja | 2026-03-06 | Not Started | Use LinkedIn Sales Navigator for list build
Phase 0: Foundation | Weeks 1–2 | Record 3-minute product demo video (Loom); embed on landing page | Marketing | Jaja | 2026-03-08 | Not Started | Show AI Copilot + multi-framework crosswalk
Phase 0: Foundation | Weeks 1–2 | Configure Calendly / booking link for discovery calls | Sales | Jaja | 2026-03-06 | Not Started | Link from landing page and LinkedIn bio
Phase 0: Foundation | Weeks 1–2 | Set up LinkedIn Sales Navigator (CISO filter: regulated industry, 250–5,000 employees) | Sales | Jaja | 2026-03-06 | Not Started | Save ICP search for weekly prospecting
Phase 0: Foundation | Weeks 1–2 | Draft 4 weeks of pre-scheduled LinkedIn content (EU AI Act, NIST AI RMF, product updates) | Marketing | Jaja | 2026-03-08 | Not Started | Buffer or Hootsuite for scheduling
Phase 0: Foundation | Weeks 1–2 | Write and schedule Show HN and Reddit launch posts (r/netsec, r/compliance) | Marketing | Jaja | 2026-03-08 | Not Started | Coordinate with GitHub publish date
Phase 0: Foundation | Weeks 1–2 | Configure analytics: Plausible or GA4 on landing page; GitHub star tracker | Infrastructure | Jaja | 2026-03-08 | Not Started
PHASE 1: PRE-LAUNCH
Phase 1: Pre-Launch | Weeks 2–4 | Begin LinkedIn outbound: 50 connection requests/week to CISO ICP | Sales | Jaja | 2026-03-15 | Not Started | Use saved ICP search in Sales Navigator
Phase 1: Pre-Launch | Weeks 2–4 | Send Day-3 follow-up messages to all accepted connections | Sales | Jaja | Rolling | Not Started | Personalize with their framework or industry
Phase 1: Pre-Launch | Weeks 2–4 | Publish LinkedIn Article 1: “EU AI Act Enforcement: What CISOs Need to Do Now” | Marketing | Jaja | 2026-03-10 | Not Started | Tag EU AI Act, NIST AI RMF hashtags
Phase 1: Pre-Launch | Weeks 2–4 | Publish LinkedIn Article 2: “Why NIST AI RMF Needs a Dedicated Tool” | Marketing | Jaja | 2026-03-17 | Not Started | Soft CTA to Community Edition
Phase 1: Pre-Launch | Weeks 2–4 | Launch Community Edition: post to Hacker News (Show HN), r/netsec, r/compliance | Marketing | Jaja | 2026-03-10 | Not Started | Time HN post for 9am EST Tuesday/Wednesday
Phase 1: Pre-Launch | Weeks 2–4 | Send 20 personalized cold emails to warm prospects (prior contacts, conference met) | Sales | Jaja | 2026-03-13 | Not Started | Use cold email template from GTM strategy doc
Phase 1: Pre-Launch | Weeks 2″4 | Join CISO Slack communities and GRC forums; introduce ControlWeave contextually | Marketing | Jaja | 2026-03-15 | Not Started | CISO Collective, Cyber Leadership Forum
Phase 1: Pre-Launch | Weeks 2″4 | Target KPI: 5 discovery calls booked | KPI | Jaja | 2026-03-22 | Not Started | Track in CRM pipeline
PHASE 2: SOFT LAUNCH
Phase 2: Soft Launch | Weeks 4–6 | Conduct first 5 discovery calls; document objections and ICP refinements | Sales | Jaja | 2026-03-29 | Not Started | Log every call outcome in CRM
Phase 2: Soft Launch | Weeks 4–6 | Convert 2+ discovery calls to 90-day Professional trial (free, no CC) | Sales | Jaja | 2026-04-05 | Not Started | Send trial activation email within 24h of call
Phase 2: Soft Launch | Weeks 4–6 | Scale LinkedIn outbound to 100 connections/week | Sales | Jaja | 2026-04-05 | Not Started | Add personalization based on recent posts
Phase 2: Soft Launch | Weeks 4″6 | Begin MSSP / consulting partner outreach: identify and contact 20 target firms | Partnerships | Jaja | 2026-04-05 | Not Started | Boutique GRC consulting firms as priority
Phase 2: Soft Launch | Weeks 4″6 | Publish weekly LinkedIn post (3x/week cadence): compliance insights + product features | Marketing | Jaja | Rolling | Not Started | Maintain content calendar in Lead Tracker
Phase 2: Soft Launch | Weeks 4″6 | Launch email newsletter (Substack/ConvertKit): “The Compliance Edge” weekly brief | Marketing | Jaja | 2026-04-01 | Not Started | Import LinkedIn connections who opt in
Phase 2: Soft Launch | Weeks 4″6 | Refine landing page based on discovery call feedback (messaging, proof points) | Marketing | Jaja | 2026-04-10 | Not Started | Add framework logos and CISO quote if available
Phase 2: Soft Launch | Weeks 4″6 | Target KPI: 20 discovery calls total, 5 paying customers, $2,500 MRR | KPI | Jaja | 2026-04-15 | Not Started | Review in weekly pipeline session
PHASE 3: FULL LAUNCH
Phase 3: Full Launch | Months 2″3 | Sign first MSSP / consulting partner; conduct joint onboarding session | Partnerships | Jaja | 2026-04-30 | Not Started | Provide co-branded one-pager
Phase 3: Full Launch | Months 2″3 | Publish first customer case study (with permission): before/after compliance story | Marketing | Jaja | 2026-05-01 | Not Started | 500-word LinkedIn article + PDF version
Phase 3: Full Launch | Months 2″3 | Launch referral program: 1 month free per paying referral | Sales | Jaja | 2026-04-20 | Not Started | Configure in Stripe or billing system
Phase 3: Full Launch | Months 2″3 | Begin Q3 2026 conference / speaking opportunity applications (RSA, GRC Summit, ISACA) | Marketing | Jaja | 2026-05-15 | Not Started | Submit 2+ speaking proposals
Phase 3: Full Launch | Months 2″3 | Review pricing: assess trial-to-paid conversion; consider introductory annual plan promo | Strategy | Jaja | 2026-05-01 | Not Started | If conversion < 10%, investigate blockers
Phase 3: Full Launch | Months 2″3 | Community Edition: respond to all GitHub issues within 24h; merge first community PRs | Infrastructure | Jaja | Rolling | Not Started | Community momentum = future leads
Phase 3: Full Launch | Months 2″3 | Monthly strategy review: channel performance, MRR, conversion rates, content analytics | Strategy | Jaja | 2026-05-01 | Not Started | Adjust channel mix based on data
Phase 3: Full Launch | Months 2″3 | Target KPI: 50 discovery calls, 50 paying customers, $20,000 MRR, 500 GitHub stars | KPI | Jaja | 2026-06-01 | Not Started | 90-day milestone review
90-DAY KPI SCORECARD
Metric | 30-Day Target | 60-Day Target | 90-Day Target | Actual (30d) | Actual (60d) | Actual (90d) | RAG Status
GitHub Stars (Community) | 150 | 350 | 500
Discovery Calls Booked | 10 | 25 | 50
Paying Customers | 5 | 20 | 50
Monthly Recurring Revenue | $2,500 | $8,000 | $20,000
LinkedIn Followers (Net New) | +200 | +500 | +1,000
Newsletter Subscribers | 250 | 600 | 1,000
MSSP Partners Signed | 0 | 1 | 3
Trial-to-Paid Conversion | n/a | 15% | 20%+

## Prospect Pipeline
CONTROLWEAVE ¦ CISO Prospect Pipeline
Primary ICP: CISOs • Mid-Market & Enterprise • Regulated Industries
Full Name | Title | Company | Industry | Company Size | Stage | Last Action | Next Step | Due Date | Notes
Sarah Mitchell | CISO | Apex Financial Group | Financial Services | 1,200 emp | New | Found via LinkedIn search | Send connection request | 2026-03-06 | Managing SOC 2 + NIST 800-53
David Okonkwo | VP of Security | HealthBridge Systems | Healthcare | 800 emp | New | Found via LinkedIn search | Send connection request | 2026-03-06 | HIPAA + NIST AI RMF exposure
Jennifer Tran | Director of GRC | ClearPath SaaS | Technology | 450 emp | New | Found via LinkedIn search | Send connection request | 2026-03-07 | SOC 2 Type II in progress
Marcus Webb | CISO | Delta Energy Corp | Energy / Utilities | 3,200 emp | New | Found via LinkedIn search | Send connection request | 2026-03-07 | NERC CIP focus
Priya Sharma | Chief Compliance Officer | NovaTech Federal | Federal Contractor | 620 emp | New | Found via LinkedIn search | Send connection request | 2026-03-08 | CMMC + NIST 800-53
PIPELINE SUMMARY (auto-update these after each weekly review)
Total Prospects in Pipeline | 0 | Discovery Calls This Week
Connected (not yet messaged) |  | Trials Active
Paying Customers |  | Pipeline MRR (est.)

## Content Calendar
CONTROLWEAVE ¦ LinkedIn + Content Marketing Calendar
3x/week LinkedIn • 1x/week Newsletter • Goal: 1,000+ impressions/post
Date | Platform | Content Pillar | Headline / Topic | Format | CTA | Status | Impressions
2026-03-10 | LinkedIn | AI Governance | EU AI Act Enforcement: What CISOs Need to Do Right Now | Article | Comment your biggest AI compliance gap | Scheduled
2026-03-12 | LinkedIn | GRC Automation | Why compliance teams are still in Excel (and how to get out) | Post | Try ControlWeave free — link in comments | Scheduled
2026-03-14 | LinkedIn | Product Feature | How ControlWeave’s AI Copilot maps 1,007 NIST controls automatically | Demo clip | Book a 15-min demo | Scheduled
2026-03-17 | LinkedIn | AI Governance | NIST AI RMF in Practice: The 4 Functions Every Security Team Needs | Article | Download our NIST AI RMF checklist | Scheduled
2026-03-19 | LinkedIn | Compliance Insight | SOC 2 vs ISO 27001 vs NIST 800-53: Which frameworks overlap (and where)? | Carousel | Tag a GRC colleague | Draft
2026-03-21 | LinkedIn | Community / Launch | We just open-sourced ControlWeave — 18 frameworks, free to deploy | Post | GitHub link in comments | Scheduled
2026-03-24 | LinkedIn | AI Governance | The EU AI Act just hit enforcement. Is your AI inventory ready? | Poll | Vote + link to ControlWeave AI monitoring | Draft
2026-03-26 | LinkedIn | GRC Automation | Audit prep used to take 6 months. Here’s how teams are cutting it to weeks | Post | Book a discovery call | Draft
2026-03-28 | LinkedIn | Product Feature | BYOK AI Copilot: Use Anthropic, OpenAI, or Google models. Your data stays yours | Demo clip | Try Community Edition free | Draft
2026-03-31 | Newsletter | Compliance Insight | The Compliance Edge #1: AI Act Week 1 enforcement roundup | Newsletter | Subscribe + share | Draft
2026-04-02 | LinkedIn | AI Governance | NIST CAISI: What the new AI Agent Standards mean for your security team | Article | Comment your questions | Draft
2026-04-04 | LinkedIn | Community / Launch | 500+ people have deployed ControlWeave. Here’s what they’re using it for | Post | Link to GitHub | Draft
2026-04-07 | Newsletter | GRC Automation | The Compliance Edge #2: How AI is compressing 6-month audit cycles | Newsletter | Subscribe | Draft

## MRR Tracker
CONTROLWEAVE ¦ MRR & Revenue Tracker
Target: $20,000 MRR by Day 90 • Pricing: Community (Free) ¦ Starter ($179) ¦ Professional ($799) ¦ Enterprise ($2,999)
Month | Starter Customers | Pro Customers | Enterprise Customers | Total Customers | Monthly MRR | MoM Growth %
March 2026 |  |  |  | 0 | 0 | n/a
April 2026 |  |  |  | 0 | 0 | n/a
May 2026 |  |  |  | 0 | 0 | n/a
June 2026 |  |  |  | 0 | 0 | n/a
July 2026 |  |  |  | 0 | 0 | n/a
August 2026 |  |  |  | 0 | 0 | n/a
September 2026 |  |  |  | 0 | 0 | n/a
October 2026 |  |  |  | 0 | 0 | n/a
November 2026 |  |  |  | 0 | 0 | n/a
December 2026 |  |  |  | 0 | 0 | n/a
90-DAY REVENUE TARGETS
30-Day MRR Target | $2,500 | 5 customers avg Starter/Pro mix
60-Day MRR Target | $8,000 | 20 customers; Pro tier adoption increases
90-Day MRR Target | $20,000 | 50 customers; first Enterprise deal